## Risk Log
Risk Identification and Description | [6 empty] | Risk Assessment |  |  |  |  | Risk Response
ID | Category | Risk Name | Risk Description & Details | Status | Identified By | Identification Date | Likelihood | Impact | Risk Level (L*I) | Risk Owner | Escalation | Risk Response Strategy | Action Details (effort & responsible) | Target Date | Traceability/Comments
RL01 | Tehnic | Configurarea SQL | Din cauza configurarii gresite a sirului de conexiune local, este posibil ca aplicatia sa nu poata accesa baza de date SQL, ceea ce va conduce la blocarea incarcarii intrebarilor. | Closed | Fratila Victor Bogdan | 01.06.2026 | 2 | 4 | 8 | Fratila Victor Bogdan | No | Reduce | Definirea unei alternative de stocare JSON si testarea timpurie a conexiunii de catre Fratila Victor Bogdan, efort 1 zi-om. | 05.06.2026 | Asociat cu problema IL3 si decizia DEC-02.
RL02 | Programare | Integrarea Design Patterns | Din cauza intelegerii deficitare a modelelor de proiectare, este posibil ca implementarea sabloanelor Strategy si Factory sa fie defectuoasa, ceea ce va conduce la intarzieri in dezvoltare. | Closed | Fratila Victor Bogdan | 01.06.2026 | 3 | 3 | 9 | Fratila Victor Bogdan | No | Reduce | Redactarea prealabila a diagramelor UML si revizuirea codului de catre Fratila Victor Bogdan, efort 2 zile-om. | 12.06.2026 | Asociat cu problema IL4 si decizia DEC-01.
RL03 | Date | Structura Date JSON | Din cauza nerespectarii formatului standard, este posibil ca fisierele JSON de quizz-uri sa fie corupte, ceea ce va conduce la exceptii de parsare la incarcarea aplicatiei. | Closed | Fratila Victor Bogdan | 01.06.2026 | 2 | 3 | 6 | Fratila Victor Bogdan | No | Reduce | Implementarea unui mecanism de validare a schemei JSON si testare de catre Fratila Victor Bogdan, efort 1 zi-om. | 06.06.2026 | Asociat cu problema IL1.
RL04 | UX/UI | Palpaire Element UI | Din cauza modului ineficient de redesenare a componentelor Windows Forms, este posibil ca interfata grafica sa palpaie frecvent, ceea ce va conduce la degradarea experientei utilizatorului. | Closed | Fratila Victor Bogdan | 01.06.2026 | 3 | 2 | 6 | Fratila Victor Bogdan | No | Reduce | Setarea proprietatii DoubleBuffered si optimizarea evenimentelor de timer de catre Fratila Victor Bogdan, efort 1 zi-om. | 13.06.2026 | Asociat cu problema IL2.
RL05 | Testare | Testare Insuficienta | Din cauza timpului limitat alocat testarii, este posibil ca unele bug-uri de calcul al scorului sa fie nedetectate, ceea ce va conduce la erori in functionare. | Closed | Fratila Victor Bogdan | 01.06.2026 | 2 | 4 | 8 | Fratila Victor Bogdan | No | Reduce | Dezvoltarea unei suite de cazuri de testare si executia lor manuala de catre Fratila Victor Bogdan, efort 2 zile-om. | 15.06.2026 | Legat de activitatea de testare finala din Project Plan.
Note on B2: The risk identifier. It should be numbered sequentially.
Note on C2: Categories of risks related to the area affected by the risk (e.g. Business, IT, People & Organisation, External and Legal, Sustainability, Data Protection, IT Security>
Note on D2: A short title for the risk.
Note on E2: A description of the risk that may occur in the project and its causes. What kind of problems will the risk result in and risk dependencies. A structured formulation of the opportunity or threat in the form of (route) Cause – Risk –Effect, along with potential risk inter-dependencies.
Note on F2: The risk status can be any of the following: Proposed: This is the initial status. Use this while the risk is still being specified. Assessing: Use this status to initiate an assessment. Waiting for Approval: Use this to request approval. Before applying this status, make sure the assessment is complete and the estimates are reliable. Approved: This status is set once the risk possibility has been accepted. Rejected: This status is set if the risk was rejected as not relevant. Closed: This status is set once the risk has been managed (e.g. mitigation )
Note on G2: The person who identifies the risk.
Note on H2: The date when the risk was identified.
Note on I2: A numeric value denoting the estimate of the probability that the risk will occur. The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on J2: A numeric value denoting the severity of the impact of the risk (should it occur). The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on K2: The risk level is the product of the likelihood and impact (RL=L*I).
Note on L2: The person accountable for the management and monitoring of this risk.
Note on M2: To be escalated to the Directing or Steering Layers: Yes or No.
Note on N2: The available strategies to deal with the identified risks are: - Avoid: risk avoidance, working the project or project plan around those conditions or activities which introduce the risk; - Reduce: risk mitigation or reduction through the proactive implementation of risk reduction activities; - Accept: acceptance of the risk. In this cases, contingency plans can also be defined in case the risk occurs; - Transfer/Share: transfer or share a risk with other entities, e.g. through insurances, sub-contracting etc.
Note on O2: Description of the action: objective of the action, scope, deliverables, person responsible and effort estimates.
Note on P2: The date that the action is expected to be implemented.
Note on Q2: The ID(s) of the task (in the Project Work Plan) implementing the risk actions, or/and the IDs of related change, issue or decisions log entries. Any additional information related to the risk approval (e.g. date) or related to the risk actions (activities).