## Issue Log
Issue Identification and Description | [6 empty] | Issue Assessment and Action Description
ID | Category | Title | Description | Status | Identified By | Identification Date | Action Details (effort & responsible) | Urgency | Impact | Size | Target Date | Issue Owner | Escalation | Traceability/Comments
IL1 | Date | Format JSON Incompatibil | Structura fisierului JSON initial nu a permis parsarea corecta a listei de optiuni de raspuns, determinand exceptii la incarcare. | Closed | Fratila Victor Bogdan | 05.06.2026 | Reformatarea structurii JSON pentru a include un array explicit de optiuni si modificarea parserului C#. | 4 | 4 | Small | 06.06.2026 | Fratila Victor Bogdan | No | Asociat cu riscul R3 (Formatarea JSON) din documentul Project Charter.
IL2 | Interfata | Palpaire Ecran Timer | Labelul timerului palpaia frecvent la fiecare secunda in timpul numaratorii inverse, afectand aspectul vizual. | Closed | Fratila Victor Bogdan | 12.06.2026 | Activarea proprietatii DoubleBuffered pe Form si utilizarea unui control optimizat pentru desenare. | 2 | 2 | Small | 13.06.2026 | Fratila Victor Bogdan | No | Identificat in timpul testarii de integrare a interfetei grafice.
IL3 | Baza de date | Conexiune SQL Blocata | Sirul de conexiune local utilizat in configuratia aplicatiei a impiedicat conectarea la instanta locala SQL Server din cauza permisiunilor de acces. | Closed | Fratila Victor Bogdan | 04.06.2026 | Modificarea parametrilor sirului de conexiune pentru a utiliza securitatea integrata Windows (Integrated Security=True). | 3 | 4 | Medium | 05.06.2026 | Fratila Victor Bogdan | No | Asociat cu riscul R1 (Configurarea SQL) din registrul de riscuri.
IL4 | Design Patterns | Integrare Strategy Dificila | Dificultati in decuplarea logicii de evaluare a scorului prin intermediul sablonului Strategy, cauzand erori la compilare. | Closed | Fratila Victor Bogdan | 10.06.2026 | Refactorizarea interfetei strategiei si definirea clara a claselor concrete pentru fiecare tip de quiz. | 3 | 3 | Medium | 11.06.2026 | Fratila Victor Bogdan | No | Asociat cu riscul R2 (Implementarea Strategy) din documentul Project Charter.
Note on C3: The issue identifier. It should be numbered sequentially.
Note on D3: Categories of issues related to the area affected by the issue (e.g. Business, IT, People & Organisation, External and Legal, Sustainability, Data Protection, IT Security, UX).
Note on E3: Short name for (describing) the issue.
Note on F3: A description of the issue and consequences of doing nothing.
Note on G3: The issue status can be any of the following: Open: the issue has been identified but no decision yet on how to resolve it. Postponed: this status is set for postponing the issue due to other priorities. Resolved: this status indicates that all necessary actions are completed and the issue is resolved. Closed: this status indicates the closing of the issue once the work is completed and verified.
Note on H3: The name of the person who identifies the issue.
Note on I3: The date that the issue has been raised.
Note on J3: Description of the recommended action, steps, deliverables, timescale, resources and effort involved.
Note on K3: A numeric value denoting the urgency of the issue. The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on L3: A numeric value denoting the severity / impact of the issue. The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on M3: Issue size represents the effort related to the issue resolution. The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on N3: The date that the issue is expected to be resolved.
Note on O3: The person accountable for the effective issue resolution.
Note on P3: To be escalated to the Directing or Steering Layers: Yes or No.
Note on Q3: The ID(s) of the task (in the Project Work Plan) implementing the issue actions, or/and the IDs of related change, risk or decisions log entries. Any additional information related to the issue actions (e.g. activities, approvals).